## Product Backlog
User Stories | Priority | Story points | Status | 112
As a database administrator, I want a documentaded data warehouse to support end-users queries | 8 | 20 | Done | 5.0909
As a database administrator, I want to see the converted log files in the database | 10 | 10 | Done | 22
As a database administrator, I want to extract new logs, query, analyse and store it in a relational database | 9 | 15 | Done
As a user, I want to have a mechanism to find the thermal locations | 7 | 12 | Done
As a administrator, I want to store the thermals in the database | 3 | 15 | Done
As a administrator, I want to see the converted weather files in the database | 5 | 10 | Done
As a user I want to visualize the results | 2 | 10 | Done
As a user I want to read about the project | 1 | 20 | Done
|  |  |  | 2018-05-18 | 112 | 112
|  |  |  | 2018-05-19 | 106.9091 | 112
|  |  |  | 2018-05-20 | 101.8182 | 112
|  |  |  | 2018-05-21 | 96.7273 | 102
|  |  |  | 2018-05-22 | 91.6364 | 102
|  |  |  | 2018-05-23 | 86.5455 | 102
|  |  |  | 2018-05-24 | 81.4545 | 102
|  |  |  | 2018-05-25 | 76.3636 | 102
|  |  |  | 2018-05-26 | 71.2727 | 102
|  |  |  | 2018-05-27 | 66.1818 | 80
|  |  |  | 2018-05-28 | 61.0909 | 80
|  |  |  | 2018-05-29 | 56 | 80
|  |  |  | 2018-05-30 | 50.9091 | 65
|  |  |  | 2018-05-31 | 45.8182 | 65
|  |  |  | 2018-06-01 | 40.7273 | 65
|  |  |  | 2018-06-02 | 35.6364 | 45
|  |  |  | 2018-06-03 | 30.5455 | 45
|  |  |  | 2018-06-04 | 25.4545 | 45
|  |  |  | 2018-06-05 | 20.3636 | 20
|  |  |  | 2018-06-06 | 15.2727 | 20
|  |  |  | 2018-06-07 | 10.1818 | 20
|  |  |  | 2018-06-08 | 5.0909 | 0

## Sprint 1
2018-05-18 | SPRINT 1 | User Stories | Status
|  | As a database administrator, I want to see the converted log files in the database | Done
Tasks
|  | Plan meetings | Done
|  | Make the flight log table design | Done
|  | Implement the flight log table | Done
|  | Implement a program that reads the log files | Done
|  | Connect the program to the database | Done
|  | Populate the database with the information | Done
|  | Test | Done
|  | Document sprint | Done

## Sprint 2
2018-05-21 | SPRINT 2 | User Stories | Status
|  | As a administrator, I want to see the converted weather files in the database | Not done
|  | Tasks | Done
|  | Make the weather log table design | Done
|  | Implement the weather log table | Done
|  | Implement a program that reads the log files | Done
|  | Connect the program to the database | Done
|  | Populate the database with the information log inforamtion | Not Done
|  | Test | Done
|  | Document sprint | Done

## Sprint 3
2018-05-24 | SPRINT 3 | User Stories | Status
|  | As a administrator, I want to see the converted weather files in the database | Done
|  | As a user, I want to have a mechanism to find the thermal locations | Done
Tasks
|  | Populate the database with the information log inforamtion | Done
|  | Test wether log converter | Done
|  | Reade flight logs from database | Done
|  | Algorithm that allocates thermals locations | Done
|  | Test | Done
|  | Document sprint | Done

## Sprint 4
2018-05-27 | SPRINT 4 | User Stories | Status
|  | As a database administrator, I want a documentaded data warehouse to support end-users queries | Not Done
|  | As a administrator, I want to store the thermals in the database | Done
Tasks
|  | Design and implement table for thermals found by program | Done
|  | Insert thermals found by program into database | Done
|  | Improve dimensional model form DWH course | Not Done
|  | Implement dimensional model | Not Done
|  | Test | Done
|  | Document sprint | Done

## Sprint 5
2018-05-30 | SPRINT 5 | User Stories | Status
|  | As a database administrator, I want a documentaded data warehouse to support end-users queries | Done
|  | As a database administrator, I want to extract data from new logs, transform them and load them in a data warehouse | Not done
Tasks
|  | Improve dimensional model form DWH course | Done
|  | Implement dimensional model | Done
|  | Implement weather ETL | Not done
|  | Implement thermal ETL | Not done
|  | Implement grid population | Done
|  | Implement D_FLIGHT population | Done
|  | Implement date pupulation | Done
|  | Test | Done
|  | Document Sprint | Done

## Sprint 6
2018-06-02 | SPRINT 6 | User Stories | Status
|  | As a user I want to visualize the results | Done
|  | As a database administrator, I want to extract new logs, query, analyse and store it in a relational database | Done
|  | Tasks | Done
|  | Implement weather ETL | Done
|  | Implement thermal ETL | Done
|  | Implement view for Power BI | Done
|  | Test | Done
|  | Document Sprint | Done

## Sprint 7
2018-06-05 | SPRINT 7 | User Stories | Status
As a user I want to read about the project
Task
|  | Make project report | Done
|  | Make process report | Done