## Product Backlog
Use Cases | User Stories | Priority | Story points | Status | 122
Dimensional Model | As a database administrator, I want a documentaded database to support end-users queries | 8 | 5 | Done | 5.5455
Extract Data | As a database administrator, I want to see the converted log files in the database | 10 | 10 | Done | 22
Implement a ETL Data Warehouse | As a database administrator, I want to extract new logs, query, analyse and store it in a relational database | 9 | 15 | Done
Find all thermals | As a user, I want to have a mechanism to find the thermal locations | 7 | 12 | Done
Store thermals | As a administrator, I want to store the thermals in the database | 3 | 15 | Not Done
Match flight with weather data | As a administrator, I want to see the converted weather files in the database | 5 | 20
Calculate average of thermal location considering the weather | As a user, I want to know the possible thermal locations | 4 | 15
Present the data in form of map | As a user I want to visualize the results | 2 | 10
Document the project | As a user I want to read about the project | 1 | 20
[5 empty] | 2018-05-18 | 122 | 122
[5 empty] | 2018-05-19 | 116.4545 | 122
[5 empty] | 2018-05-20 | 110.9091 | 122
[5 empty] | 2018-05-21 | 105.3636 | 122
[5 empty] | 2018-05-22 | 99.8182 | 122
[5 empty] | 2018-05-23 | 94.2727 | 122
| As a user, I want to know the possible thermal locations |  |  |  | 2018-05-24 | 88.7273 | 122
| As a user I want to visualize the results |  |  |  | 2018-05-25 | 83.1818 | 122
| As a user I want to read about the project |  |  |  | 2018-05-26 | 77.6364 | 122
[5 empty] | 2018-05-27 | 72.0909 | 122
[5 empty] | 2018-05-28 | 66.5455 | 122
[5 empty] | 2018-05-29 | 61 | 122
[5 empty] | 2018-05-30 | 55.4545 | 122
[5 empty] | 2018-05-31 | 49.9091 | 122
[5 empty] | 2018-06-01 | 44.3636 | 122
[5 empty] | 2018-06-02 | 38.8182 | 122
[5 empty] | 2018-06-03 | 33.2727 | 122
[5 empty] | 2018-06-04 | 27.7273 | 122
[5 empty] | 2018-06-05 | 22.1818 | 122
[5 empty] | 2018-06-06 | 16.6364 | 122
[5 empty] | 2018-06-07 | 11.0909 | 122
[5 empty] | 2018-06-08 | 5.5455 | 122

## Sprint 1
2018-05-18 | SPRINT 1 | User Stories | Status
|  | As a database administrator, I want to see the converted log files in the database | Done
Tasks
|  | Plan meetings | Done
|  | Make the database design and mapping | Done
|  | Implement the database | Done
|  | Implement a program that reads the log files | Done
|  | Connect the program to the database | Done
|  | Implement a method that finds a flight log and separates its different information | Done
|  | Populate the database with the information | Done
|  | Test | Done
|  | Document sprint | Done

## Sprint 2
2018-05-21 | SPRINT 2 | User Stories | Status
|  | As a administrator, I want to see the converted weather files in the database | Not done
Tasks
|  | Weather log converter | Done
|  | Thermal finder | Not done
|  | Test | Done
|  | Document sprint | Done

## Sprint 3
2018-05-24 | SPRINT 3 | User Stories | Status
|  | As a administrator, I want to see the converted weather files in the database | Done
|  | As a user, I want to have a mechanism to find the thermal locations | Done
Tasks
|  | Weather log converter | Done
|  | Thermal finder | Done
|  | Test | Done
|  | Document sprint | Done

## Sprint 4
2018-05-27 | SPRINT 4 | User Stories | Status
|  | As a database administrator, I want a documentaded database to support end-users queries | Not Done
|  | As a administrator, I want to store the thermals in the database | Done
Tasks

## Sprint 5
2018-05-30 | SPRINT 5 | User Stories | Status
|  | As a database administrator, I want a documentaded database to support end-users queries | Done
|  | As a database administrator, I want to extract new logs, query, analyse and store it in a relational database | Not done
Tasks

## Sprint 6
2018-06-02 | SPRINT 6 | User Stories | Status
|  | As a database administrator, I want a documentaded database to support end-users queries | Done
|  | As a database administrator, I want to extract new logs, query, analyse and store it in a relational database | Not done
Tasks